## Report
Vehicle Status ¦ management report
AAOS-first reuse MVP / DAR-SDV-VS-001 v1.1 / proposal for approval
Change blue cells on Inputs. This report recalculates in Excel; scope stays fixed.
REDUCED DEMO / WEEK | FULL MVP / WEEK |  | WITH RESERVE / WEEK
8 | 18 |  | 20
Selected team: 2 developers (1 experienced + 1 junior). Full-scope work remains 828 accepted-work hours. Timing changes; acceptance requirements do not.
FORECAST CHECKPOINTS
Checkpoint | End week | Approx. finish | Target week | Variance | Schedule
Recovery / Gate A | 2 | 2026-09-27 | - | - | Forecast
Core / Gate B | 5 | 2026-10-18 | - | - | Forecast
Reduced demo | 8 | 2026-11-08 | 8 | 0 | WITHIN
Full MVP / Gate C | 18 | 2027-01-17 | 18 | 0 | WITHIN
With reserve | 20 | 2027-01-31 | - | - | Forecast
SCOPE AND DECISION
Reduced demo | Mapping A -> same core -> MQTT/TLS -> receiver receipt. No full-reuse, durable-crash-recovery or remote-configuration claim yet.
Full MVP | Mappings A/B + MQTT/HTTPS; bounded durable recovery; one authorized profile update; S1-S6; frozen core and target-port design. Not an AAOS SDV runtime port.
Staffing envelope | 1440 |  | 1600
Decision requested: approve recovery only (2.0 active weeks; 2.0 elapsed weeks including waits). Re-estimate at Gate A before committing to the remaining forecast.
Forecast is not approval or evidence. Dates use elapsed calendar weeks; availability and waits must reflect real access, leave and assignments. All full-MVP cases still require a recorded pass. Scope/detail: companion short DAR.
Model check | OK - formula consistency; estimates need review
Formulas:
Approx. finish = IF([FULL MVP / WEEK]="","",Inputs!C19+ROUNDUP([FULL MVP / WEEK]*Inputs!C25,0)-1)

## Inputs
Change the team, not the report
Edit blue cells. Black cells calculate. Default team: 1 experienced developer + 1 intern/fresher.
1 TEAM
Total developers | 2 | Changing 2 to 3 adds one experienced developer unless the junior count also changes.
Intern / fresher count | 1 | Must be smaller than total developers. At least one experienced developer is required.
Experienced developer count | 1 | Total minus intern/fresher count. Assumes suitable AAOS/core skills.
Paid hours per person / week | 40 | Nominal time; not all time becomes accepted delivery work.
Experienced allocation | 100% | Share of working time assigned to this project.
Junior allocation | 100% | Set below 100% for part-time internship or other assignments.
2 USABLE CAPACITY
Experienced usable time, before mentoring | 85% | 85% of allocated time. The remaining 15% covers coordination and environment/support.
Junior accepted work rate, after recovery | 60% | 60% of allocated time; includes tests and evidence accepted after review.
Junior accepted work rate, during recovery | 30% | Lower rate applies to the whole recovery phase, not a fixed number of weeks.
Mentoring hours per allocated junior / week | 6 | Deducted once from the experienced pool; ordinary PR review stays inside work estimates.
Maximum experienced contributors per phase | 2 | Caps useful parallel work. More staff do not automatically remove sequence or review limits.
Maximum junior contributors per phase | 2 | Caps parallel support work. These contributor caps are proposed controls.
3 CALENDAR AND FORECAST
Planning start date | 2026-09-14 | Illustrative start only. Replace with an approved start after access is ready.
Desired reduced-demo week | 8 | A comparison target, not a formula override or promise.
Desired full-MVP week | 18 | A comparison target, not a formula override or promise.
Sponsor-controlled reserve (weeks) | 2 | Added after the base forecast. Does not buy extra features.
Schedule rounding step (weeks) | 0.5 | Rounds each phase upward. Use 0.5 or 1 week.
Work estimate multiplier | 1 | 1.00 = source workload. 1.20 models 20% more work; does not change scope.
Calendar days per elapsed week | 7 | Calendar dates are approximate elapsed-week dates, not a holiday-aware workday schedule.
4 CALCULATED CAPACITY
Experienced pool: delivery hours / week | 28 | Before the per-phase contributor and senior-critical caps.
Experienced: delivery hours per person | 28 | Mentoring is shared across the experienced pool.
Junior: hours per person after recovery | 24 | Used for phases P2-P9.
Junior: hours per person during recovery | 12 | Used for phase P1 only.
Nominal allocated team hours / week | 80 | Staffed/allocated hours, not accepted work. Used for the staffing envelope.
Input validation | OK | If BLOCKED, correct the inputs before using any forecast.
No overtime, new production backend, independent security reviewer or completed AAOS SDV runtime port is assumed. Role changes alter the forecast, not the approved scope.
Note on C5: SDV_Vehicle_Status_DAR_EN_v1_0_One_Senior_One_Junior.md, sections 20-20B: planning assumptions, not measured productivity. Changing 2 to 3 adds one experienced developer unless the junior count also changes.
Note on C6: SDV_Vehicle_Status_DAR_EN_v1_0_One_Senior_One_Junior.md, sections 20-20B: planning assumptions, not measured productivity. Must be smaller than total developers. At least one experienced developer is required.
Note on C8: SDV_Vehicle_Status_DAR_EN_v1_0_One_Senior_One_Junior.md, sections 20-20B: planning assumptions, not measured productivity. Nominal time; not all time becomes accepted delivery work.
Note on C9: SDV_Vehicle_Status_DAR_EN_v1_0_One_Senior_One_Junior.md, sections 20-20B: planning assumptions, not measured productivity. Share of working time assigned to this project.
Note on C10: SDV_Vehicle_Status_DAR_EN_v1_0_One_Senior_One_Junior.md, sections 20-20B: planning assumptions, not measured productivity. Set below 100% for part-time internship or other assignments.
Note on C12: SDV_Vehicle_Status_DAR_EN_v1_0_One_Senior_One_Junior.md, sections 20-20B: planning assumptions, not measured productivity. 85% of allocated time. The remaining 15% covers coordination and environment/support.
Note on C13: SDV_Vehicle_Status_DAR_EN_v1_0_One_Senior_One_Junior.md, sections 20-20B: planning assumptions, not measured productivity. 60% of allocated time; includes tests and evidence accepted after review.
Note on C14: SDV_Vehicle_Status_DAR_EN_v1_0_One_Senior_One_Junior.md, sections 20-20B: planning assumptions, not measured productivity. Lower rate applies to the whole recovery phase, not a fixed number of weeks.
Note on C15: SDV_Vehicle_Status_DAR_EN_v1_0_One_Senior_One_Junior.md, sections 20-20B: planning assumptions, not measured productivity. Deducted once from the experienced pool; ordinary PR review stays inside work estimates.
Note on C16: Proposed workbook scheduling control; validate at Gate A. Caps useful parallel work. More staff do not automatically remove sequence or review limits.
Note on C17: Proposed workbook scheduling control; validate at Gate A. Caps parallel support work. These contributor caps are proposed controls.
Note on C19: Proposed workbook scheduling control; validate at Gate A. Illustrative start only. Replace with an approved start after access is ready.
Note on C20: SDV_Vehicle_Status_DAR_EN_v1_0_One_Senior_One_Junior.md, sections 20-20B: planning assumptions, not measured productivity. A comparison target, not a formula override or promise.
Note on C21: SDV_Vehicle_Status_DAR_EN_v1_0_One_Senior_One_Junior.md, sections 20-20B: planning assumptions, not measured productivity. A comparison target, not a formula override or promise.
Note on C22: SDV_Vehicle_Status_DAR_EN_v1_0_One_Senior_One_Junior.md, sections 20-20B: planning assumptions, not measured productivity. Added after the base forecast. Does not buy extra features.
Note on C23: Proposed workbook scheduling control; validate at Gate A. Rounds each phase upward. Use 0.5 or 1 week.
Note on C24: Proposed workbook scheduling control; validate at Gate A. 1.00 = source workload. 1.20 models 20% more work; does not change scope.

## Plan
Delivery plan ¦ same scope, variable team
Blue cells are editable work estimates and scheduling controls. Phases run in order; expert/support work can overlap inside each phase.
Forecast only. Pass evidence must be reviewed at the gate; a calculated finish date never means that a test passed. Expert = experienced developer. Support = work a junior can do under review.
ID | Phase | Expert-only work (h) | Support work (h) | Minimum weeks | Expert lead slots | Waiting weeks | Duration weeks | Finish week | Finish date | Checkpoint | Required evidence | Junior pool h/w | Expert critical h/w | Expert total h/w | Combined h/w | Raw duration | Start offset weeks | Phase input check
P1 | Recover the AAOS PoC | 56 | 24 | 2 | 1 | 0 | 2 | 2 | 2026-09-27 | Gate A | Build, data access, dependencies, target risks and revised estimate. | 12 | 28 | 28 | 40 | 2 | 0 | OK
P2 | Define contract and core | 56 | 48 | 1 | 2 | 0 | 2 | 4 | 2026-10-11 | Core foundation | Agree signal meaning, triggers and ports; prepare deterministic tests. | 24 | 28 | 28 | 52 | 2 | 2 | OK
P3 | Approve the portable core | 28 | 24 | 1 | 1 | 0 | 1 | 5 | 2026-10-18 | Gate B | S1-S2 pass; same-core host build; no Android/provider types in core. | 24 | 28 | 28 | 52 | 1 | 4 | OK
P4 | Bind the AAOS adapters | 28 | 24 | 1 | 1 | 0 | 1 | 6 | 2026-10-25 | AAOS integration | Vehicle reads, lifecycle, permissions and mapping A use the core. | 24 | 28 | 28 | 52 | 1 | 5 | OK
P5 | Demonstrate MQTT path | 56 | 36 | 1 | 2 | 0 | 2 | 8 | 2026-11-08 | Reduced demo | Mapping A -> core -> MQTT/TLS -> receiver receipt. Downlink stays off. | 24 | 28 | 28 | 52 | 2 | 6 | OK
P6 | Prove HTTPS replacement | 56 | 40 | 1 | 2 | 0 | 2 | 10 | 2026-11-22 | S3 | Both paths preserve canonical data, IDs, decisions and receipt meaning. | 24 | 28 | 28 | 52 | 2 | 8 | OK
P7 | Prove offline recovery | 84 | 56 | 2 | 2 | 0 | 3 | 13 | 2026-12-13 | S4 | Bounded durable queue; crash/restart; retry, expiry and loss accounting. | 24 | 28 | 28 | 52 | 3 | 10 | OK
P8 | Secure one configuration | 48 | 30 | 1 | 1 | 0 | 2 | 15 | 2026-12-27 | S5 | Authorized profile update; reject replay/bad input; no vehicle writes. | 24 | 28 | 28 | 52 | 1.7143 | 13 | OK
P9 | Prove reuse and hand over | 64 | 70 | 2 | 2 | 0 | 3 | 18 | 2027-01-17 | Gate C / D-Design | A/B x MQTT/HTTPS; S1-S6; freeze, runbook and substantiated port design. | 24 | 28 | 28 | 52 | 2.5769 | 15 | OK
| BASE TOTAL | 476 | 352 |  |  | 0 | 18 | 18 | 2027-01-17
Work is not the same as staffed time. Default estimates total 828 accepted-work hours; nominal staffing includes mentoring, learning, coordination and capacity that cannot always be used on the critical path.
Phase duration = round up the largest of: minimum weeks, expert-only work / expert lead capacity, or all work / combined capacity. Waits are then added. Expert capacity can cover support work without being counted twice.
Source: DAR v1.0, sections 12-20B. P3/P4 split the W5-W6 source workload equally. Expert lead slots, minimum weeks, parallel caps, rounding and waiting controls are proposed model assumptions. All estimates need Gate A review.
Formulas:
Finish date = IF([Finish week]="","",Inputs!$C19+ROUNDUP([Finish week]*Inputs!$C25,0)-1)
Finish date = IF([Finish week]="","",J17)
Note on C9: SDV_Vehicle_Status_DAR_EN_v1_0_One_Senior_One_Junior.md, section 20B, phase loading. P3/P4 split W5-W6 equally; total remains 476 expert + 352 support hours. Original junior-work estimate is treated as shared work; experienced developers may cover it.
Note on D9: SDV_Vehicle_Status_DAR_EN_v1_0_One_Senior_One_Junior.md, section 20B, phase loading. P3/P4 split W5-W6 equally; total remains 476 expert + 352 support hours. Original junior-work estimate is treated as shared work; experienced developers may cover it.
Note on E9: Proposed resource-model control, not a new scope requirement. Minimum duration protects discovery/integration/testing time. Waiting is additive calendar delay before this phase.
Note on F9: Proposed resource-model control, not a new scope requirement. Minimum duration protects discovery/integration/testing time. Waiting is additive calendar delay before this phase.
Note on G9: Proposed resource-model control, not a new scope requirement. Minimum duration protects discovery/integration/testing time. Waiting is additive calendar delay before this phase.
Note on C10: SDV_Vehicle_Status_DAR_EN_v1_0_One_Senior_One_Junior.md, section 20B, phase loading. P3/P4 split W5-W6 equally; total remains 476 expert + 352 support hours. Original junior-work estimate is treated as shared work; experienced developers may cover it.
Note on D10: SDV_Vehicle_Status_DAR_EN_v1_0_One_Senior_One_Junior.md, section 20B, phase loading. P3/P4 split W5-W6 equally; total remains 476 expert + 352 support hours. Original junior-work estimate is treated as shared work; experienced developers may cover it.
Note on E10: Proposed resource-model control, not a new scope requirement. Minimum duration protects discovery/integration/testing time. Waiting is additive calendar delay before this phase.
Note on F10: Proposed resource-model control, not a new scope requirement. Minimum duration protects discovery/integration/testing time. Waiting is additive calendar delay before this phase.
Note on G10: Proposed resource-model control, not a new scope requirement. Minimum duration protects discovery/integration/testing time. Waiting is additive calendar delay before this phase.
Note on C11: SDV_Vehicle_Status_DAR_EN_v1_0_One_Senior_One_Junior.md, section 20B, phase loading. P3/P4 split W5-W6 equally; total remains 476 expert + 352 support hours. Original junior-work estimate is treated as shared work; experienced developers may cover it.
Note on D11: SDV_Vehicle_Status_DAR_EN_v1_0_One_Senior_One_Junior.md, section 20B, phase loading. P3/P4 split W5-W6 equally; total remains 476 expert + 352 support hours. Original junior-work estimate is treated as shared work; experienced developers may cover it.
Note on E11: Proposed resource-model control, not a new scope requirement. Minimum duration protects discovery/integration/testing time. Waiting is additive calendar delay before this phase.
Note on F11: Proposed resource-model control, not a new scope requirement. Minimum duration protects discovery/integration/testing time. Waiting is additive calendar delay before this phase.
Note on G11: Proposed resource-model control, not a new scope requirement. Minimum duration protects discovery/integration/testing time. Waiting is additive calendar delay before this phase.
Note on C12: SDV_Vehicle_Status_DAR_EN_v1_0_One_Senior_One_Junior.md, section 20B, phase loading. P3/P4 split W5-W6 equally; total remains 476 expert + 352 support hours. Original junior-work estimate is treated as shared work; experienced developers may cover it.
Note on D12: SDV_Vehicle_Status_DAR_EN_v1_0_One_Senior_One_Junior.md, section 20B, phase loading. P3/P4 split W5-W6 equally; total remains 476 expert + 352 support hours. Original junior-work estimate is treated as shared work; experienced developers may cover it.
Note on E12: Proposed resource-model control, not a new scope requirement. Minimum duration protects discovery/integration/testing time. Waiting is additive calendar delay before this phase.
Note on F12: Proposed resource-model control, not a new scope requirement. Minimum duration protects discovery/integration/testing time. Waiting is additive calendar delay before this phase.
Note on G12: Proposed resource-model control, not a new scope requirement. Minimum duration protects discovery/integration/testing time. Waiting is additive calendar delay before this phase.
Note on C13: SDV_Vehicle_Status_DAR_EN_v1_0_One_Senior_One_Junior.md, section 20B, phase loading. P3/P4 split W5-W6 equally; total remains 476 expert + 352 support hours. Original junior-work estimate is treated as shared work; experienced developers may cover it.
Note on D13: SDV_Vehicle_Status_DAR_EN_v1_0_One_Senior_One_Junior.md, section 20B, phase loading. P3/P4 split W5-W6 equally; total remains 476 expert + 352 support hours. Original junior-work estimate is treated as shared work; experienced developers may cover it.
Note on E13: Proposed resource-model control, not a new scope requirement. Minimum duration protects discovery/integration/testing time. Waiting is additive calendar delay before this phase.
Note on F13: Proposed resource-model control, not a new scope requirement. Minimum duration protects discovery/integration/testing time. Waiting is additive calendar delay before this phase.
Note on G13: Proposed resource-model control, not a new scope requirement. Minimum duration protects discovery/integration/testing time. Waiting is additive calendar delay before this phase.
Note on C14: SDV_Vehicle_Status_DAR_EN_v1_0_One_Senior_One_Junior.md, section 20B, phase loading. P3/P4 split W5-W6 equally; total remains 476 expert + 352 support hours. Original junior-work estimate is treated as shared work; experienced developers may cover it.
Note on D14: SDV_Vehicle_Status_DAR_EN_v1_0_One_Senior_One_Junior.md, section 20B, phase loading. P3/P4 split W5-W6 equally; total remains 476 expert + 352 support hours. Original junior-work estimate is treated as shared work; experienced developers may cover it.
Note on E14: Proposed resource-model control, not a new scope requirement. Minimum duration protects discovery/integration/testing time. Waiting is additive calendar delay before this phase.
Note on F14: Proposed resource-model control, not a new scope requirement. Minimum duration protects discovery/integration/testing time. Waiting is additive calendar delay before this phase.
Note on G14: Proposed resource-model control, not a new scope requirement. Minimum duration protects discovery/integration/testing time. Waiting is additive calendar delay before this phase.
Note on C15: SDV_Vehicle_Status_DAR_EN_v1_0_One_Senior_One_Junior.md, section 20B, phase loading. P3/P4 split W5-W6 equally; total remains 476 expert + 352 support hours. Original junior-work estimate is treated as shared work; experienced developers may cover it.
Note on D15: SDV_Vehicle_Status_DAR_EN_v1_0_One_Senior_One_Junior.md, section 20B, phase loading. P3/P4 split W5-W6 equally; total remains 476 expert + 352 support hours. Original junior-work estimate is treated as shared work; experienced developers may cover it.
Note on E15: Proposed resource-model control, not a new scope requirement. Minimum duration protects discovery/integration/testing time. Waiting is additive calendar delay before this phase.
Note on F15: Proposed resource-model control, not a new scope requirement. Minimum duration protects discovery/integration/testing time. Waiting is additive calendar delay before this phase.
Note on G15: Proposed resource-model control, not a new scope requirement. Minimum duration protects discovery/integration/testing time. Waiting is additive calendar delay before this phase.
Note on C16: SDV_Vehicle_Status_DAR_EN_v1_0_One_Senior_One_Junior.md, section 20B, phase loading. P3/P4 split W5-W6 equally; total remains 476 expert + 352 support hours. Original junior-work estimate is treated as shared work; experienced developers may cover it.
Note on D16: SDV_Vehicle_Status_DAR_EN_v1_0_One_Senior_One_Junior.md, section 20B, phase loading. P3/P4 split W5-W6 equally; total remains 476 expert + 352 support hours. Original junior-work estimate is treated as shared work; experienced developers may cover it.
Note on E16: Proposed resource-model control, not a new scope requirement. Minimum duration protects discovery/integration/testing time. Waiting is additive calendar delay before this phase.
Note on F16: Proposed resource-model control, not a new scope requirement. Minimum duration protects discovery/integration/testing time. Waiting is additive calendar delay before this phase.
Note on G16: Proposed resource-model control, not a new scope requirement. Minimum duration protects discovery/integration/testing time. Waiting is additive calendar delay before this phase.
Note on C17: SDV_Vehicle_Status_DAR_EN_v1_0_One_Senior_One_Junior.md, section 20B, phase loading. P3/P4 split W5-W6 equally; total remains 476 expert + 352 support hours. Original junior-work estimate is treated as shared work; experienced developers may cover it.
Note on D17: SDV_Vehicle_Status_DAR_EN_v1_0_One_Senior_One_Junior.md, section 20B, phase loading. P3/P4 split W5-W6 equally; total remains 476 expert + 352 support hours. Original junior-work estimate is treated as shared work; experienced developers may cover it.
Note on E17: Proposed resource-model control, not a new scope requirement. Minimum duration protects discovery/integration/testing time. Waiting is additive calendar delay before this phase.
Note on F17: Proposed resource-model control, not a new scope requirement. Minimum duration protects discovery/integration/testing time. Waiting is additive calendar delay before this phase.
Note on G17: Proposed resource-model control, not a new scope requirement. Minimum duration protects discovery/integration/testing time. Waiting is additive calendar delay before this phase.

## Scenarios
Compare team sizes
The scope and work estimates stay the same. Scenarios use all other current Inputs and Plan assumptions.
The first row follows Inputs. Other rows are editable examples, not staffing recommendations. A larger junior team can increase the senior mentoring load and delay expert-critical work.
Scenario | Experienced | Junior | Total | Demo week | Full MVP week | With reserve week | Nominal allocated hours | Interpretation
Current inputs | 1 | 1 | 2 | 8 | 18 | 20 | 1440 | Live forecast for the selected team. | OK | 28 | 28 | 24 | 12 | 2 | 2 | 1 | 1 | 2 | 2 | 3 | 2 | 3
2 developers | 1 | 1 | 2 | 8 | 18 | 20 | 1440 | Editable comparison; role mix is shown in columns B-C. | OK | 28 | 28 | 24 | 12 | 2 | 2 | 1 | 1 | 2 | 2 | 3 | 2 | 3
3 developers | 2 | 1 | 3 | 7 | 14.5 | 16.5 | 1740 | Expert lead capacity and support work both constrain the forecast. | OK | 62 | 31 | 24 | 12 | 2 | 1.5 | 1 | 1 | 1.5 | 1.5 | 2 | 2 | 2
4 developers | 3 | 1 | 4 | 7 | 14 | 16 | 2240 | Phase caps and gate time limit further acceleration. | OK | 96 | 32 | 24 | 12 | 2 | 1.5 | 1 | 1 | 1.5 | 1.5 | 2 | 1.5 | 2
2 developers | 2 | 0 | 2 | 7.5 | 15 | 17 | 1200 | Experienced staff also cover the support workload. | OK | 68 | 34 | 0 | 0 | 2 | 2 | 1 | 1 | 1.5 | 1.5 | 2.5 | 1.5 | 2
3 developers | 1 | 2 | 3 | 12 | 24.5 | 26.5 | 2940 | Mentoring is deducted before expert-critical capacity is calculated. | OK | 22 | 22 | 48 | 24 | 3 | 3 | 1.5 | 1.5 | 3 | 3 | 4 | 2.5 | 3
HOW TO READ THE COMPARISON
Dates and staffed hours are calculated; scope, quality gates and the selected idea are not automatically changed. These are planning forecasts, not measured productivity or a promise that all experienced developers have interchangeable skills.
To model 2 -> 3 developers in the active plan: set Inputs!C5 to 3 and leave Inputs!C6 at 1. To add a junior instead, set both total developers and junior count. Review the role mix, not only the total.
The model applies one team from the planning start. It does not model mid-project joining dates or actual progress. For an in-flight reforecast, save a baseline copy and review remaining work and capacity with the senior lead.

## Guide
Read me ¦ model and sources
The workbook is the single source for changing resources, forecast dates and the management report.
USE THE WORKBOOK
Change the team | Inputs!C5 = total developers; C6 = juniors. Experienced count is calculated. Example: 3 total and 1 junior means 2 experienced developers.
Review capacity | Check allocation, accepted-work rates and mentoring. Defaults reproduce the v1.0 assumptions: 28 experienced hours/week; junior 12 in recovery and 24 after recovery.
Review forecast | Report shows milestones, schedule variance and allocated hours. Plan shows phase calculations. Scenarios compares role mixes without changing the active plan.
Edit the estimate | Plan blue cells change work, minimum duration, critical lead slots and waits. Inputs!C24 applies one work multiplier. Save a baseline copy before changing estimates.
Share the report | Print the Report tab or use it during the meeting. Excel formulas update without macros or scripts. The .md and .docx contain stable idea/detail, not a synchronized date snapshot.
WHAT THE MODEL DOES
Capacity | Experienced pool = people x paid hours x allocation x usable-time rate minus allocated-junior mentoring. Split mentoring evenly across the experienced pool.
Work assignment | Expert-only work cannot be delegated to juniors. Support work may be done by juniors or spare experienced capacity; total work is counted once.
Duration | For each phase, take MAX(minimum weeks, expert work / expert critical capacity, all work / combined capacity). Multiply work by the estimate factor and round up to the selected step.
Sequence and waits | Phases are sequential. Roles may work together within a phase. Waiting weeks are added before that phase; the team is assumed allocated through waits and reserve.
Scope and limits | No automatic feature removal, gate pass or initiative switch. No holiday calendar, individual join dates, actual-progress tracking, overtime or independent assurance. Larger teams require a lead review of parallel-work caps.
TRACEABILITY AND APPROVAL
Planning source [P1] | SDV_Telematics_Vehicle_Status_AAOS_First_Plan_Revision_EN.md: AAOS-first baseline, core separation, mapping/cloud substitutions, S1-S6 and claim limits.
Resource source [P2] | SDV_Vehicle_Status_DAR_EN_v1_0_One_Senior_One_Junior.md: sections 20 and 20B supply the capacity assumptions and 476 expert / 352 junior-work hours. Sections 2A-3A supply the Automotive alternatives.
Model additions | Phase W5-W6 split equally for the Gate B checkpoint. Junior work becomes a shared-work pool. Phase floors, contributor caps, rounding, scenario staffing and wait controls are editable modeling assumptions, not measured facts.
Baseline reconciliation | Default inputs yield recovery week 2, core Gate B week 5, reduced demo week 8, full MVP week 18 and reserve endpoint week 20. These reconcile to the prior proposal; they are not approved dates.
Approvals still needed | Sponsor confirms objective, people, start, capacity and funding. Senior validates workload, skills, semantics, security and gate evidence. Re-estimate after recovery; record accepted deviations.