## Data
No | Question | Answer | Correct | Explain | Note | Domain

## Sheet2 (hidden)
| Init | plan | execute | monitor & control | close
Integrate | Create project charter | Plan project management | manage & direct work | monitor & control work | close project or phase
|  |  | manage knowledge | Perform integrated change control
Scope |  | Plan scope management |  | Control scope
|  | Collect requirement |  | Valid scope
Define scope
|  | Create WBS |  | Control schedule
Schedule |  | Plan schedule management
Create activities list
sequence activites
estimate activities duration
Cereate schedule
Cost |  | Plan cost management |  | Control cost
Estimate cost
Determine budget
Quality |  | Plan quality management | manage quality | control quality
Resource |  | Plan resource management | Aquire resource | Control resouce
|  | Estimate activities resource | Manage resource
Develop human resource
Risk |  | Plan risk management | Implement risk response | Monitor risk
Identify risks
Perform qualitative risks
Perform quantitative risk
Plan risk response
Procument |  | Plan procument management | Conduct procument | Monitor & Control procument
Communication |  | Plan communication management | manage communication | Control communication
Stakeholder | Identify stakeholders | Plan stakeholder engagement | Manage stakeholder engagement | Monitor stakeholoder engagement

## Agile Principles
Agile Manifesto | Scrum Pillars
Individual and communiation over process and tools | Transparent
Working software over comprehenship documentations | Inspection
Customer collaboration over contract negotiation | Adaption
Respone to change over follow plan
Scrum Value
12 Principles | Focus
We statisfy our customer with great system by frenquently delviver | commitment
Welcome change | encourage
Deliver frequently | open
Working with customer | respect
build project around motivated individual
face 2 face communication
Working software is primary process mesurement
maitain sustainable pace
maintain design
Simplicity
team create architecture
Reflect and adjust

## Problem detection & Resolution
Understanding problems | Identify problem as soon as possible Cost of change Technical dept: solution is refactoring, daily hygiene Create a Save and Open Environment Failure Modes: We make mistakes, we prefer to fail conservatively, we prefer to invent rather than research,we are creatures of habit, we are inconsistent success Modes: good at looking around, able to learn, malleable, take pride in our work success strategies: balance discipline with tolerance, start with someting concrete and tangible, copy and alter, watch and listen, support both concentration and communication, match work assignment with the person
detecting problems | Lead Time: entire life cycle, cycle time: start dev till finish (start enter 'end' column). Respone time = lead time - cycle time Cycle time=WIP/thoughput Project cycle time: how long the entire project will take, from start to finish Throughput & productivity: throughput=average amount of work in a time period. Productivity: the rate of efficiency at which the work is done - such as the amount of work done per team member
Defect: defect rate, escape defect
Variance Analysis: Causes of variation: common cause & special cause
Trend Analysis:
Control Limit
managing threads & issues | risk adjusted backlog: Creating the risk-adjusted backlog with EMV (expected monetary value)
risk severity= risk probability * risk impact
Risk burndown graph
solving problem | as continuous improvement
Engage the team
Some problems can be solved

## Team Performance
Building agile team | Development Team/ Delivery Team | - Build the product increments, using agile practices and process - Regulary update information radiators to share their progress with stakeholders - Self organize and self direct their working progress within an interation - Share their process with each other in daily stand-up meetings. - Write acceptance tests for the product increments - Test and revise the product increments until they pass the acceptance tests - Demonstrate the completed product increment to the customer in the interation review meeting. - Hold interation retrospectives to reflect on their process and continually improve it - Perform release and interation planning, including estimating the stories and tasks
| Product owner/ Customer/ Proxy Customer/ Value Management Team/ Business Representative | Maximize the value of the product by choosing and prioritizing the product features. Manages the product backlog, making sure that is accurate, up to date, and prioritized by business value Makes sure the team has a shared understanding of the backlog items and the value they are supposed to deliver Provides the acceptance criteria that the delivery team will use to prepare acceptance tests Determines whether each completed product increment is working as intended, and either accepts it or request changes (in the interation review meeting) May change the product features and their priority at any time Facilitates the engagement of external project stakeholders and manage their expectations. Provides the due dates for the project and/ or it's releases. Attends planning meetings, reviews, and retrospectives
| Scrum Master | Acts as a servant leader to the delivery team, helping them improve and remove bariers to their progress. Helps the delivery team self-govern and self-organize, instead of governing and organizing them Serves as a facilitator and conduit for communication within the delivery team and with other stakeholders Make sure the delivery team's plan is visible and its progress is radiated to stakeholders. Acts as a coach and mentor to the delivery team Guides the team's agile process and make sure their agile practices are being used properly Help the product owner manage the product backlog Helps the product owner communicate the product vision, goals, and backlog items to the delivery team. Facilitates meetings (planning, reviews, and retrospectives) Follows up on issues raised in stand-up meetings to remove impediments so that the team can stay ontrack
| Project Sponsor | Serves as the project's main advocate within the organization Provide direction to the product owner role about the organization's overall goals for the project Focuses on the big picture of whether the project will deliver the expected value on time and on budget. Is invited to the interation review meetings to see the product increments as the are completed, but might not to attend
| Cross function team | I shaped & T shaped Empowered Teams: self-organizing & selft directing empowering & encouraging emergent leadership Create a safe place for experiments Constructive disagreemnt
| Model of team development | Shu-ha-ri: shu-"keep, protect, maintain", ha-"detech or break free", ri-"go beyond or transcend" Dreyfus: novice, advanced beginer, competent, proficient, expert; Tuckman - adaptive leadership: forming-leading;storming-coaching;norming-supporting;peforming-delegating
| Training, coaching, mentoring | Team coaching in events, individual coaching in progress
Team motivation
Create collaborative team spaces | Colocated Team
| Team space | Caves and common. Colocaated, small size and common space make easy to share tatic knowledge by osmotic communication
| Distributed team | start by holding a face-face kickoff meeting;digital tools
Tracking team performance | Burndowns chart
burnup chart
Cummulative flow diagram (CFD)
Velocity tracking chart

## Continuous Improvement (hidden)
Kaizen | Change for the better: Plan -Do-Check-Act
Agile Cycle | Plan Develop Evaluate Learn
Multi Level of Improvement | Pair programming -> Daily Stand up-> Demo, review, retrospective-> Product release
Process improvement | Process Tailoring | Kanban is tailoring-friendly Scrum is less keen on tailoring. Scrum makes recommendation about how to transform the enterprise into an agile enviroment
| Hybird model | Agile-agile: Scrum - XP; Scrum - Kanban=> Scrumban Agile - traditional
| System thinking | Different leve of complexity on Projects
| Process Analysis | Anti-pattern: One size for all projects, Intolerant, heavy, Embellished, untried, Used once Success criteria: Project got shipped, leadership remained intact, the team would work the same way again Success patterns: Interactive, face-2-face communication, Excess methodology weight is costly, Greater criticality requrie greater ceremoney, feedback and communication reduce the need for intermediate deliverables, discipline, skills, understanding counter process, formality and documentation, efficiency is expendable in nonbottleneck ativities;
| Value streaming mapping | Total Cycle time=Value-added time+nonevalue-added time; Process cycle efficiency=value-added time/ total cycle time;
| Project pre-mortems | Image the failure=>Generate the reasons=> consolidate the list=> revisit the plan
Product improvement | Review | Plan - do -check-act (Plan-develop-evaluate-learn) Let the data speak for itself Respect individuals Diverge then converge
| Product feedback loops and learning Cycles | Pair programming-seconds Unit Test-minutes Customer collaboration - hours Stand-up meeting - days Iteration demo - weeks Release - Months
| Feed back method | IKIWISI - I know it when I see it
| Approved Iterations | iteration reviews
People improvement | Retrospective | Improved productivity Improved capability improved quality improved capacity
| Retrospective process | Set the stage | check in Focus on/ focus off ESVP Working agreement
|  | Gather data | Timeline Triple nickels color code Dots Mad, Sad, Glad Locate Strengths Satisfaction Histogram Team Radar Like to like
|  | Generate insights | brain storming five whys fishbone analysis Prioritize with dots Identify themes
|  | Decide what to do | short subjects: start doing/ stop doing/ do more of/ do less of SMART Goals Circle of Questions Restrspective planning game
|  | Close the retrospective | Plus/ Delta - what we sholud do more (good) / what should change (not well) Helped, Hindered, hypothesis Return on time invested (ROTI) Appreciation
| Team self-assessments | Shore's Team self assessment scoring model | Thinking Collaborating Releasing Planning Developing
|  | Tabaka's team self assessment model | Self-organization Empowered to make decisions Belief in vision and success committed team Trust each other Participatory decision making Consensus-driven Constructive disagreement